## Sheet1
Issue	Begin Date	End Date
Installation of Mongo DB, Tomcat, Java and Development Tool	06/24/16	07/01/16
Build UI for Login	07/01/16	07/08/16
Build UI for Logout	07/08/16	07/15/16
Build HomePage	07/15/16	07/22/16
Build Java code for Upload File	07/22/16	07/29/16
Build Java Code for Listing File	07/29/16	07/06/16
Build Java Code for Downloading File	08/06/16	08/08/16
Refactoring	08/09/16	Ongoing
Refactoring UI	08/09/16	Ongoing
Validations	08/09/16	Ongoing